## 2k22
Engr. Abul Kalam Library
Yearly Objective and Action Plan
YEARLY OBJECTIVE 2022:
Implementation of KOHA Software for the Library Management System (LMS)
Legend
Planned
ACTION PLAN: | [10 empty] | Deviation |  | 20%
S. #. | Activities | Responsible Person | 2022
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | KOHA awareness session of the Library Officers/IT Managers by External Trainer/Expert | Librarian | bar: 2022 Jan to 2022 Feb
2 | Formation of the Committee and defining scope | Librarian | bar: 2022 Feb to 2022 Mar
3 | Visits of libraries for demonstration of KOHA | Committee | bar: 2022 Mar to 2022 Apr
4 | Assessing & developing compatibility of library functions with KOHA (policy updation subject to requirement) | Committee | bar: 2022 Mar to 2022 Aug
5 | Migration of Library Data of different Modules etc. | Committee | bar: 2022 Aug to 2022 Oct
6 | Test Run | Committee | bar: 2022 Oct to 2022 Dec