## 2K20
Engr. Abul Kalam Library
Yearly Objective and Action Plan
YEARLY OBJECTIVE 2023:
Optimization of the Koha Software for the Library Management System (LMS) | [10 empty] | Legend
Planned
ACTION PLAN: | [10 empty] | Deviation |  | 20%
S. #. | Activities | Responsible Person | 2023
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Merging of multiple copies of titles in the Library Catalogue | Concerned Section Incharges
2 | Merging of issues of Journals/Magazines in the Library Catalogue | Incharge Serial Section
3 | Entrying of Journals Articles in the Koha Module | Incharge Serial Section
4 | Entrying of Non-book material information the Library Catalogue | ITM (JE) / Incharge Book Bank
5 | Barcoding on books of the Book Bank | Incharge Book Bank
6 | Updating the Catalogue Enrichment Tool for Koha Library OPAC | Concerned Section Incharges
7 | Troubleshooting of Realtime problems in Koha | ITM (JE) / Concerned Section Incharges
8 | Testing of Koha Google Authentication | ITM (JE)
9 | Development and Integration of plugs-ins* | ITM (JE) /Concerned Section Incharges
10 | Development of Reports for different Modules including Special Data Reports for ISO/HEC/PEC etc. | ITM (JE)
11 | Testing & Reporting of Account Management Module | ITM (JE) / Concerned Section Incharges
12 | Koha Trainings to the Library Patrons | ITM (JE)
* Plug-Ins::
Clearance and Semester Registration
Single Sign On
Web Reporting from Koha
Self Registration of Students

## Sheet2
Engr. Abul Kalam Library
Yearly Objective and Action Plan
YEARLY OBJECTIVE 2020:
"SWOT analysis of Engr. Abul Kalam Library with the two benchmark libraries in the region"
Legend
Planned
ACTION PLAN: | [10 empty] | Deviation |  | 20%
S. #. | Activities | Responsible Person | 2020
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Formation of the committee | Librarian | bar: 2020 Feb
2 | Defining scope and stretegies to analyse | Committee | bar: 2020 Mar
3 | Selection of libraries for benchmark | bar: 2020 Mar
4 | Development of Questionaire | bar: 2020 Mar
5 | Conduct survey for DataCollection and Compilation ofcollected data | Committee | bar: 2020 Apr to 2020 May
6 | Conduct SWOT analysis of two bencmarking libraires | Committee | bar: 2020 Jun to 2020 Jul
7 | Conduct SWOT analsis of AKL | Committee | bar: 2020 Aug to 2020 Sep
8 | Comparative study & finalization | Committee | bar: 2020 Oct to 2020 Nov
7 | Compilation | Librarian | bar: 2020 Dec