## 2K20
Engr. Abul Kalam Library
Yearly Objective and Action Plan
YEARLY OBJECTIVE 2021:
"SWOT analysis of Engr. Abul Kalam Library with the two benchmark libraries in the region" (Revised)
Legend
Planned
Completed in 2020
ACTION PLAN: | [9 empty] | Deviation |  |  | 20%
S. #. | Activities | Responsible Person | 2021
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Formation of the Committee and defining scope | Librarian | 2021 Jun: Activities completed in the year 2020
2 | Development of questionnaire | Committee | bar: 2021 Mar to 2021 May
3 | Review and finalization of questionnaire | DDQEC-I / Committee | bar: 2021 Jan to 2021 Feb
4 | Visits of libraries and collection of data | Committee | bar: 2021 Mar to 2021 May
5 | Conduct SWOT analysis and comparision | Committee | bar: 2021 Jun to 2021 Sep
6 | Recommendation & finalization | Committee | bar: 2021 Oct to 2021 Dec

## Sheet2
Engr. Abul Kalam Library
Yearly Objective and Action Plan
YEARLY OBJECTIVE 2020:
"SWOT analysis of Engr. Abul Kalam Library with the two benchmark libraries in the region"
Legend
Planned
ACTION PLAN: | [10 empty] | Deviation |  | 20%
S. #. | Activities | Responsible Person | 2020
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Formation of the committee | Librarian | bar: 2020 Feb
2 | Defining scope and stretegies to analyse | Committee | bar: 2020 Mar
3 | Selection of libraries for benchmark | bar: 2020 Mar
4 | Development of Questionaire | bar: 2020 Mar
5 | Conduct survey for DataCollection and Compilation ofcollected data | Committee | bar: 2020 Apr to 2020 May
6 | Conduct SWOT analysis of two bencmarking libraires | Committee | bar: 2020 Jun to 2020 Jul
7 | Conduct SWOT analsis of AKL | Committee | bar: 2020 Aug to 2020 Sep
8 | Comparative study & finalization | Committee | bar: 2020 Oct to 2020 Nov
7 | Compilation | Librarian | bar: 2020 Dec